16-09-24
F2F Meeting

---
Updates on the literature review
- Produced a draft on Friday 13th
- Structure needed serious revising and refocussing on literature relevant to the project
- 13th – 17th/18th refocussing the literature review.
- Details in the next slides

---
Literature Review Structure (Before)
- Structure originally consisted of 4 chapters
- Chapter 1 had too much detail about T2DM and Prediabetes (8 pages)
- Chose to condense important relevant details into an introductory paragraph in the lit review.

---
Literature Review Structure (Before)
- The structure previously focussed on a cell to cell level, missing relevant larger ideas in the literature

---
Literature Review Structure (Before)
- Too much detail on multiomics, not enough detail on scRNA-seq describing why I am choosing the methods I am using.

---
Literature Review Structure (Before)
- This section remains in the literature review although I am finding it hard to connect it to my project …

---
Literature Review Structure (Now)
- Literature Review now 3 chapters

---
Literature Review Structure (Now)
- Refocussed on scRNA-seq, upstream / downstream techniques

---
Literature Review Structure (Now)
??

---
Problems
Unsure how chapter 3 fits into the project

---
Timeline
- 17th / 18th first complete draft
- Sunday 22nd results / methods complete
- Saturday 28th Final Draft complete